## ProjectSchedule
VIDEO PRODUCTION SCHEDULE |  | Project Start: |  | 2019-04-08
|  | Display Week: |  | 1 |  |  | 2019-04-08 | [6 empty] | 2019-04-15 | [6 empty] | 2019-04-22 | [6 empty] | 2019-04-29 | [6 empty] | 2019-05-06 | [6 empty] | 2019-05-13 | [6 empty] | 2019-05-20 | [6 empty] | 2019-05-27
 | time axis 2019-04-08 to 2019-06-02
TASK | EXPENSES | WHO | PROGRESS | START | END | DAYS | time axis 2019-04-08 to 2019-06-02
Pre-Production Phase
Develop a Story Concept (determine theme or underlying message) | 0 | SAR | 0% | 2019-04-08 | 2019-04-15
Write a one sentence Synopsis of Story Concept (aka Logline) | 0 | SAR | 0% | 2019-04-08 | 2019-04-15
Write a Story Outline (aka Treatment) | 0 | SAR | 0% | 2019-04-15 | 2019-04-22
Write a Script (include Character Worksheet) | 0 | SAR | 0% | 2019-04-22 | 2019-04-29
Generate a Storyboard (based upon the Script) | 0 | SAR | 0% | 2019-04-29 | 2019-05-06
Crew selection & hire | 0 | SAR | 0% | 2019-04-29 | 2019-05-06
Cast auditions, selection & hire | 0 | SAR | 0% | 2019-05-04 | 2019-05-04
Research weather conditions on proposed shooting days | 0 | SAR | 0% | 2019-05-06 | 2019-05-06
Compile a Shooting Schedule (detailed scene by scene breakdown used during Production Phase) | 0 | SAR | 0% | 2019-05-06 | 2019-05-13
Compile Research/RECCE Notes and reconnaissance performed on shooting location(s) | 0 | SAR | 0% | 2019-05-06 | 2019-05-13
Compile an Equipment & Props Listing | 0 | SAR | 0% | 2019-05-06 | 2019-05-13
Compile a Required B-Roll Footage Listing | 0 | SAR | 0% | 2019-05-06 | 2019-05-13
Generate & distribute Release Forms (Crew, Cast, Music & Location) | 0 | SAR | 0% | 2019-05-13 | 2019-05-20
Put in place any required location Permits | 0 | SAR | 0% | 2019-05-13 | 2019-05-13
Put in place any required government related training and/or certification (e.g. Workplace Health & Safety) | 0 | SAR | 0% | 2019-05-13 | 2019-05-13
Purchase Insurance Cover for Production Phase | 100 | SAR | 0% | 2019-05-13 | 2019-05-13
Generate Daily Call Sheets | 0 | SAR | 0% | 2019-05-13 | 2019-05-20
Select, and/or acquire equipment, props, products & costumes | 0 | SAR | 0% | 2019-05-14 | 2019-05-19
Host a Cast 'Conscious Contact' Preparation Day (includes makeup trial, hair trial, costume fitting, rehearsal/round-table reading, return of signed permission forms, Workplace Health and Safety training/briefing & presentation of Daily Call Sheet(s)) | 100 | SAR CAST CAE | 0% | 2019-05-18 | 2019-05-18
Host a Crew 'Conscious Contact' Preparation Day (includes Shooting Script reading, general direction, character descriptions (visual & personality), overall tone of 'Conscious Contact' Short Film, return of signed permission forms, Workplace Health and Safety training/briefing & presentation of Daily Call Sheet(s)) | 50 | SAR MRE | 0% | 2019-05-19 | 2019-05-19
Production Phase
Prepare Sets and other locations (e.g. parking area, public facilities, SD cards, PC storage), clean up/rubbish removal, furniture removal/addition, video/audio equipment check, natural lighting check & ensure that there is a sufficient amount of media storage | 0 | SAR MRE | 0% | 2019-05-20 | 2019-05-24
Production Day 1 (Full Cast):
Set preparation (prop placement, lighting adjustment, equipment adjustment & final checks) | 0 | MRE | 0% | 2019-05-25 | 2019-05-25
Cast preparation (hair, makeup and costume) | 0 | CAE | 0% | 2019-05-25 | 2019-05-25
Layout refreshment buffett | 50 | CAE | 0% | 2019-05-25 | 2019-05-25
Directors Roundtable (ease any concerns, answer any direction questions & form a circle for group hug) | 0 | SAR CAST | 0% | 2019-05-25 | 2019-05-25
Shoot footage (Production Day 1) | 0 | SAR MRE CAST | 0% | 2019-05-25 | 2019-05-25
Check the rushes | 0 | SAR | 0% | 2019-05-25 | 2019-05-25
Manage safe storage & backup of footage | 0 | SAR | 0% | 2019-05-25 | 2019-05-25
Day 2 (Full Cast):
Set preparation (prop placement, lighting adjustment, equipment adjustment & final checks) | 0 | SAR MRE | 0% | 2019-05-26 | 2019-05-26
Cast preparation (hair, makeup and costume) | 0 | CAE | 0% | 2019-05-26 | 2019-05-26
Layout refreshment buffett | 50 | CAE | 0% | 2019-05-26 | 2019-05-26
Directors Roundtable (ease any concerns, answer any direction questions & form a circle for group hug) | 0 | SAR CAST | 0% | 2019-05-26 | 2019-05-26
Shoot footage (Production Day 2) | 0 | SAR MRE CAST | 0% | 2019-05-26 | 2019-05-26
Check the rushes | 0 | SAR | 0% | 2019-05-26 | 2019-05-26
Manage safe storage & backup of footage | 0 | SAR | 0% | 2019-05-26 | 2019-05-26
Day 3 (B-Roll Footage - Extras):
Set preparation (prop placement, lighting adjustment, equipment adjustment & final checks) | 0 | SAR MRE | 0% | 2019-05-27 | 2019-05-27
Layout sandwich platter and beverages for 2 | 20 | CAE | 0% | 2019-05-27 | 2019-05-27
Shoot any additonal footage (refer to Required B-Roll Footage Listing) | 0 | SAR MRE | 0% | 2019-05-27 | 2019-05-27
Check the rushes | 0 | SAR | 0% | 2019-05-27 | 2019-05-27
Manage safe storage & backup of footage | 0 | SAR | 0% | 2019-05-27 | 2019-05-27
Backup Days 4 & 5 (Select Cast) (only to be used if unable to shoot on days above):
Set preparation (prop placement, lighting adjustment, equipment adjustment & final checks) | 0 | SAR MRE | 0% | 2019-06-01 | 2019-06-02
Cast preparation (hair, makeup and costume) | 0 | CAE | 0% | 2019-06-01 | 2019-06-02
Layout refreshment buffett | 100 | CAE | 0% | 2019-06-01 | 2019-06-02
Shoot any additonal footage not captured on Day 1, 2 or 3 | 0 | SAR MRE CAST | 0% | 2019-06-01 | 2019-06-02
Check the rushes | 0 | SAR | 0% | 2019-06-01 | 2019-06-02
Manage safe storage & backup of footage | 0 | SAR | 0% | 2019-06-01 | 2019-06-02
Post-Production Phase
Assemble the footage (video and audio) into a single Video in correct sequence of events | 0 | SAR | 0% | 2019-05-28 | 2019-05-29
Edit the Video content focussing on one element each time | 0 | SAR | 0% | 2019-05-30 | 2019-06-02
Add Front & End Credit sequences (don't forget 5 Second black screen) | 0 | SAR | 0% | 2019-06-03 | 2019-06-03
Add Graphics & Special Visual Effects | 0 | SAR | 0% | 2019-06-03 | 2019-06-05
Correct Video colour (colour grading) | 0 | SAR | 0% | 2019-06-03 | 2019-06-05
Add or adjust audio (sound design, automated dialog replacement, mixing & music composition) | 0 | SAR | 0% | 2019-06-06 | 2019-06-07
Record & add Voiceover | 0 | SAR | 0% | 2019-06-06 | 2019-06-07
Ensure that both Video & Audio are in sync | 0 | SAR | 0% | 2019-06-08 | 2019-06-08
Lock the Picture! | 0 | SAR | 0% | 2019-06-08 | 2019-06-08
Distribution Phase
Export the Video into a 1080p HD file format | 0 | SAR | 0% | 2019-06-09 | 2019-06-09
Upload the Video to a suitable YouTube Channel (set video visibility to Unlisted) | 0 | SAR | 0% | 2019-06-09 | 2019-06-09
Embed Video inside Creative Journal (append the Synopsis, Script and a personal reflection on the project) | 0 | SAR | 0% | 2019-06-10 | 2019-06-10
Assist UniSA teaching staff re: an online screening for peers | 0 | SAR PEERS | 0% | 2019-06-11 | 2019-06-23
Organise a Premiere Screening for crew, cast, family & friends | 250 | SAR | 0% | 2019-06-29 | 2019-06-29
| Legend: SAR CAE MRE | Sharon Ann Rowland (Director) Courtney Ann Eaton (Costume Manager & Caterer) Madison Ann Eaton (Crew)
Optional Tasks:
Pre-Production Phase
→ Generate a Marketing & Distribution Strategy for 'Conscious Contact' Short Film
→ Generate a more in depth Production Budget for Pre-Production, Production, Post-Production & Distribution Phases
→ Generate a Production Schedule to track Production Budget expenditure
→ Ensure all approvals relating to the Shooting Schedule, the Production Schedule and Workplace Health & Safety have occurred
Distribution Phase
→ Promote 'Conscious Contact' Short Film via pre-defined Marketing & Distribution Strategy

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.